## Sheet1
Phase | Task | Status
Phase 1 – Backend Setup | Install dependencies (express, mongoose, cors, dotenv) | DONE
Phase 1 – Backend Setup | Connect to MongoDB (db.js) | DONE
Phase 1 – Backend Setup | Create basic models: Bookmark, Prompt | DONE
Phase 1 – Backend Setup | Add REST API routes for bookmarks and prompts (GET, POST, DELETE) | DONE
Phase 1 – Backend Setup | Test APIs with Postman | DONE
Phase 2 – Frontend Setup | Install dependencies (react-router-dom, axios, tailwindcss) | DONE
Phase 2 – Frontend Setup | Create pages: Home, Bookmarks, Prompts | PENDING
Phase 2 – Frontend Setup | Create components: Navbar, BookmarkList, PromptList, SearchBar | PENDING
Phase 2 – Frontend Setup | Connect frontend to backend via Axios | TO DO
Phase 3 – UI Polish | Add Tailwind styling | PENDING
Phase 3 – UI Polish | Add Dark/Light mode toggle | TO DO
Phase 3 – UI Polish | Simple responsive design | TO DO
Phase 4 – Optional Features | Add authentication (Clerk/Auth0/Firebase) | TO DO
Phase 4 – Optional Features | Add ChatGPT API integration for prompt execution | TO DO
Phase 4 – Optional Features | Add code snippet storage | TO DO